## Sheet1
Risk Matrix |  | Impact
|  | Negligible | Minor | Major | Hazardous | Catastrophic
Liklihood | Very Unlikely | Low | Low | Low medium | Medium | Medium
| Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
| Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
| Likely | Low | Low medium | Medium | Medium high | High
| Very Likely | Low medium | Medium | Medium high | High | High
Risk | Risk Statement | Response strategy | Objectives | Likelihood | Impact | Risk Level
Sensitive data uploaded to GitHub repo | Uploaded info may contain sensitive data such as usernames or passwords. This could be used maliciously by hackers and be a serious threat to users and the system. | Use strong username and passwords as well as saving them only in a file that will be added to the .gitignore file. The passwords should be updated regularly so that if they are still uploaded then they will not be usable. | Reduces both the chances of a data link and of being hacked. | Likely | Minor | Low
Internet Issues/outage | Without internet it is not possible to push to the remote repo meaning new dependencies will not be available and document will be difficult to acquire | Have multiple ways to connect to the internet to prevent this being a single point of failure. This can be done by using a mobile hotspot or even going to a cafe for free wifi. | Reduces downtime to the internet if primary source is unavailable. | Unlikely | Major | Low medium
Power Issues/Outage | Without power it is not possible to work on the documents from my PC | Having multiple machines or using a laptop can prevent this as it can be taken to a facility that has not had a power outage | Reduces downtime if power is unavailable | Unlikely | Hazardous | Medium
Accidental overwrite and push | Pushing changes accidentally could result in non working code going live | Commiting often at working points of code | This gives us commit points we can revert our commit back to in case of accidental pushes | Likely | Negligible | Low
RSI | Wrists could be strained from poor desk setup and too many hours working | Move wrists at timed intervals, making sure to take breaks and rest when tired | This will make sure I am not sore the next day or future and can continue to work effectively | Very Unlikely | Minor | Low
Health problems | Health problems that lead to needing rest or being hospitalised will halt all time spent by the dev on the project that may cause a significant delay | While possibly unavoidable, you can still ensure that a workspace is clean and avoid contact with persons who may have covid. Avoid dangerous physical activities that could result in injury | To stay healthy during the project time and keep work on track for completion time | Unlikely | Hazardous | Medium
GitHub site down | Something may happen to the GitHub site causing it to be down for a period of time meaning you cannot clone the repo down or push anything to it | Ensure you have a working repo saved locally to carry on working from and push changes up to GitHub when it comes back online | To ensure as little down time as possible | Unlikely | Catastrophic | Medium HIgh